## GDSP HIE-Prod Entrance Criteria
GDSP HIE Production: Entrance Criteria for Go/No-Go Meeting
# | Phase | Entity | Criteria | Supporting Document(s) | Primary Contact | Completion Date
1 | Planning | GDSP HIE Partner Deloitte Consulting | Weekly touch-point calls held with project management and technical teams from HIE partners, GDSP, and Deloitte
2 | Design | GDSP HIE Partner Deloitte Consulting | Requirements sessions completed with key stakeholders, which included: - Review of HL7 message structure for NBS results - Review of Acknowledgment message structure - Data transmission flow between GDSP and HIE partners | GDSP HIE - NBS Interface Requirements for HIE Partners which includes all documents from Step 2- Implementation onboarding packet
3 | Development & Testing | HIE Partner | Development of Interface for exchange of NBS results. | All the development & testing activities listed in Detailed Progress Checklist from Step 1 - Getting Started onboarding packet
4 | Interface Testing | GDSP HIE Partner Deloitte Consulting | Tested the functionality of exchanging newborn screening results and acknowledgements between GDSP and HIE Receiver in pre-production environment. Issues identified have been discussed and will be fixed appropriately in upcoming release
5 | Go-Live | GDSP HIE Partner | Resources are identified and available for Production deployment
6 | Go-Live | Deloitte Consulting | Deloitte resources identified and will be available via email/phone during Go-Live Activities | Meeting invites for daily calls during 1st week of production
7 | Go-Live | HIE Partner | HIE Partner stakeholders have reviewed and signed forms for NBS electronic results transmission | Refer consent forms from Step 3 - Closure onboarding packet